## Explanations
Since many measures require internal resources for implementation, we need to get the overall picture of general demands and availabilities of the requested people.
Therefore, please list all internal resources for measure implementation in the Resource_Planning sheet that are on average at least required for
  0.2 FTE (~1 day per week) over a period of 3 months
  or
  0.1 FTE over a period of 1 year
Once the necessary resources for implementation are identified, please already align with the respective department/team and persons in order to secure the allocation to your measure.
There will be two loops in order to avoid conflicts concerning internal resources within the ProFlex pipeline and/or already running projects. Please observe the following deadlines:
  Jul 31st - Loop 1: All projects (measures >=50 keur impl. cost)
  Aug 21st - Loop 2: All projects (if adjustments since Loop 1) + all other measures
  Aug 31st - Finalized resource planning

## Resource_Planning
Please indicate internal resource need for your measures |  |  |  | Contact: | [7 empty] | Needed monthly capacity in FTE
Measure ID | Measure Title | Role | Other Role (please specify) | Department (on team level if possible) | Booking Status | Average monthly FTE | Total needed FTE | Start date | End date | Duration (years) | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01
FF-ww-0329 | abcde | Project Manager |  | F/HG-DE | Approved | 0.72 | 1.081 | 2020-07-01 | 2021-12-31 | 1.5014 | 0.72 | 0.72 | 0.72 | 0.72 | 0.72 | 0.72 | 0.72 | 0.72 | 0.72 | 0.72 | 0.72 | 0.72 | 0.72 | 0.72 | 0.72 | 0.72 | 0.72 | 0.72
FF-ww-0329 | abcde | Project Manager |  | F/HG-DE | Approved | 0.85 | 1.2762 | 2020-07-01 | 2021-12-31 | 1.5014 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85
FF-ww-0329 | abcde | Project Manager |  | F/HG-DE | Open | 0.6 | 0.90082 | 2020-07-01 | 2021-12-31 | 1.5014 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6
FF-ww-0329 | abcde | Project Manager |  | F/HG-DE | Approved | 0.25 | 0.37534 | 2020-07-01 | 2021-12-31 | 1.5014 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
FF-ww-0329 | abcde | Global Handling - Referent |  | F/HG-P | Open | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FF-ww-0329 | abcde | Business Analyst - Referent | (Lars Müller / one of his team members) | F/XG-I | Open | 0.1 | 0.099726 | 2020-07-01 | 2021-06-30 | 0.99726 | 2020-07-01: 0.1; 2020-08-01: 0.1; 2020-09-01: 0.1; 2020-10-01: 0.1; 2020-11-01: 0.1; 2020-12-01: 0.1; 2021-01-01: 0.1; 2021-02-01: 0.1; 2021-03-01: 0.1; 2021-04-01: 0.1; 2021-05-01: 0.1; 2021-06-01: 0.1
FF-ww-0329 |  |  |  |  | Open
FF-ww-0329 |  | Project Manager |  | F/HG-DE | Approved | 0.15 | 0.22521 | 2020-07-01 | 2021-12-31 | 1.5014 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15
FF-ww-0329 |  | Project Manager |  | F/HG-DE | Open | 0.25 | 0.37534 | 2020-07-01 | 2021-12-31 | 1.5014 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
FF-ww-0329 | abcde | IT Business Process - Referent |  | F/IA-H | Pending | 0.1 | 0.099726 | 2021-01-01 | 2021-12-31 | 0.99726 | 2021-01-01: 0.1; 2021-02-01: 0.1; 2021-03-01: 0.1; 2021-04-01: 0.1; 2021-05-01: 0.1; 2021-06-01: 0.1; 2021-07-01: 0.1; 2021-08-01: 0.1; 2021-09-01: 0.1; 2021-10-01: 0.1; 2021-11-01: 0.1; 2021-12-01: 0.1
FF-ww-0329 | abcde | IT Business Process - Referent |  | F/IA-H | Pending | 0.1 | 0.099726 | 2021-01-01 | 2021-12-31 | 0.99726 | 2021-01-01: 0.1; 2021-02-01: 0.1; 2021-03-01: 0.1; 2021-04-01: 0.1; 2021-05-01: 0.1; 2021-06-01: 0.1; 2021-07-01: 0.1; 2021-08-01: 0.1; 2021-09-01: 0.1; 2021-10-01: 0.1; 2021-11-01: 0.1; 2021-12-01: 0.1
FF-ww-0375 |  | Project Manager |  | F/HG-DE | Approved | 0.85 | 1.2762 | 2020-07-01 | 2021-12-31 | 1.5014 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85
FF-ww-0375 |  | Project Manager |  | F/HG-DE | Approved | 0.25 | 0.37534 | 2020-07-01 | 2021-12-31 | 1.5014 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
FF-ww-0375 |  | Project Manager |  | F/HG-DE | Open | 0.4 | 0.60055 | 2020-07-01 | 2021-12-31 | 1.5014 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4
FF-ww-0375 |  | Project Manager |  | F/HG-DE | Approved | 1 | 1.5014 | 2020-07-01 | 2021-12-31 | 1.5014 | bar: 2020-07-01 to 2021-12-01
FF-ww-0375 |  | Business Analyst - Referent | F/HS colleague? | F/HS | Open | 0.2 | 0.30027 | 2020-07-01 | 2021-12-31 | 1.5014 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
FF-ww-0375 |  | Business Analyst - Referent |  | F/HG-P | Open
FF-ww-0375 |  | IT Business Process - Referent |  | F/IA-H | Pending | 0.43333 | 0.65059 | 2020-07-01 | 2021-12-31 | 1.5014 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4
FF-ww-0375 |  | IT Business Process - Referent |  | F/IA-H | Pending | 0.43333 | 0.65059 | 2020-07-01 | 2021-12-31 | 1.5014 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4
FF-ww-0375 |  | Operational Ground Production - Expert |  | F/XU | Pending | 1 | 0.99726 | 2020-07-01 | 2021-06-30 | 0.99726 | bar: 2020-07-01 to 2021-06-01
FF-ww-0375 |  | Operational Ground Production - Expert |  | F/XS | Open | 0.75 | 0.74795 | 2021-01-01 | 2021-12-31 | 0.99726 | 2021-01-01: 0.75; 2021-02-01: 0.75; 2021-03-01: 0.75; 2021-04-01: 0.75; 2021-05-01: 0.75; 2021-06-01: 0.75; 2021-07-01: 0.75; 2021-08-01: 0.75; 2021-09-01: 0.75; 2021-10-01: 0.75; 2021-11-01: 0.75; 2021-12-01: 0.75
FF-ww-0375 |  | Operational Ground Production - Expert |  | F/XW | Open | 0.75 | 1.126 | 2020-07-01 | 2021-12-31 | 1.5014 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75
FF-ww-0375 |  | Operational Ground Production - Expert |  | F/XE | Open | 0.5 | 0.75068 | 2020-07-01 | 2021-12-31 | 1.5014 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
FF-ww-0375 |  | Operational Ground Production - Expert |  | F/XL | Open
FF-ww-0375 |  | Operational Ground Production - Expert |  | F/XM | Open
FF-ww-0375 |  | Handling Frankfurt |  | F/HF-LE | Open | 0.2 | 0.30027 | 2020-07-01 | 2021-12-31 | 1.5014 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
FF-ww-0374 | e-RFS | Projektmanagement - PL |  | F/HG-DE | Approved | 1 | 1.5014 | 2020-07-01 | 2021-12-31 | 1.5014 | bar: 2020-07-01 to 2021-12-01
FF-ww-0374 | e-RFS | Global Handling - Referent |  | F/HG | Open | 1 | 1.5014 | 2020-07-01 | 2021-12-31 | 1.5014 | bar: 2020-07-01 to 2021-12-01
FF-ww-0374 | e-RFS | IT Business Process - Referent | Project Management IT | F/IA-H | Pending | 0.5 | 0.75068 | 2020-07-01 | 2021-12-31 | 1.5014 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
FF-ww-0374 | e-RFS | IT Business Process - Referent | Business Analyst | F/IA-H | Pending | 0.5 | 0.75068 | 2020-07-01 | 2021-12-31 | 1.5014 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
FF-ww-0374 |  | IT Business Process - Referent | Business Analyst | F/IA-H | Pending | 1 | 1.5014 | 2020-07-01 | 2021-12-31 | 1.5014 | 0.5 | 2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1 | 1 | 1 | 1 | 0.8 | 0.8 | 0.5 | 0.5 | 0.5
FF-ww-0374 |  | IT Business Process - Referent | Architect IT | F/IA-H | Pending | 0.5 | 0.75068 | 2020-07-01 | 2021-12-31 | 1.5014 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3
FF-ww-0374 | e-RFS | Handling Support - Referent |  | F/HF-LS | Pending | 0.5 | 0.75068 | 2020-07-01 | 2021-12-31 | 1.5014 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
FF-ww-0374 |  | Handling Frankfurt |  | F/HF-LE | Open | 0.1 | 0.15014 | 2020-07-01 | 2021-12-31 | 1.5014 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
FF-ww-0374 | e-RFS | Handling Frankfurt |  | F/HF-LE | Open | 0.3 | 0.45041 | 2020-07-01 | 2021-12-31 | 1.5014 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.2 | 0.3 | 0.2 | 0.3 | 0.2 | 0.3 | 0.2 | 0.3 | 0.2 | 0.3 | 0.2 | 0.3
FF-ww-0374 |  | Handling Frankfurt |  | F/HF-LE | Open | 0.1 | 0.15014 | 2020-07-01 | 2021-12-31 | 1.5014 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
FF-ww-0374 |  | Handling Frankfurt |  | F/HF | Open | 0.1 | 0.15014 | 2020-07-01 | 2021-12-31 | 1.5014 | 0 | 0.1 | 0.1 | 0 | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
FF-ww-0374 | e-RFS | Global Handling - Referent |  | F/HG-P | Open | 0.15 | 0.22521 | 2020-07-01 | 2021-12-31 | 1.5014 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0.1 | 0 | 0.1 | 0 | 0.1 | 0 | 0.1 | 0 | 0.1 | 0 | 0.1
FF-ww-0374 | e-RFS | Recht / Politik / Strategie / Umwelt - Referent |  | F/CJ-R | Pending
Note on G2: 0.2 FTE (~1 day per week) over a period of 3 months or 0.1 FTE over a period of 1 year

## Parameter (hidden)
ID | Title | Roles
FF-HF-0289 | Automated I-Punkt | Business Analyst - Referent
FF-HF-0402 | Optimize GLP maintenance contract | Commercial Analyst
FF-HF-0403 | Reorganize Customs Team | Controlling - Referent
FF-HF-0404 | Process efficiencies ("AlfaReloaded Lean") | Controlling - TL
FF-HF-0405 | Insource Counter CAL | Customer Feedback / Services - Referent
FF-HF-0409 | Consolidate commercial and work safety mgmt. | Customer Feedback / Services - TL
FF-HF-0412 | auto PLAR 2.0 | Digital Transformation
FF-HF-0413 | Reduce tasks in "A07 Team" (F/HF) | Einkauf - Referent
FF-HF-0414 | Reduce 1 FTE in Handling Support | Einkauf - TL
FF-HF-0415 | Establish "Springerkonzept" on a commercial basis | Finance & Accounting - Referent
FF-HF-0430 | Change CCTV Provider | Finance & Accounting - TL
FF-HF-0431 | Outsource loading accessories storage to Jettainer | Fleetmanagement - Referent
FF-HF-0432 | Reduce 4 FTE at F/HF-TM | Fleetmanagement - TL
FF-HF-0433 | Optimize routing maintenance | Flight Ops - Fliegerischer Referent
FF-HF-0434 | Optimize "Flurförderfahrzeug" (FFZ) fleet | Flight Ops - Referent
FF-HF-0435 | Integrate FCTL RFS in load planning | Flight Ops - TL
FF-HF-0436 | Automated Scale | Global Handling - Referent
FF-HF-0438 | Reorganize steering within F/HF-W | Global Handling - TL
FF-HG-0226 | Re-negotiate Bosch Contract (Cust. Feedb. Mgmt) | Handling Frankfurt
FF-HG-0227 | CST EMEA – all markets “in-scope” | Handling Support - Referent
FF-HG-0296 | Revise Delvag service contract for liability claims by insurance companies | Handling Support - TL
FF-HS-0299 | Optimize Security Measures | HR - Referent
FF-HS-0305 | Automate security inspection DHL FRA | HR - TL
FF-HS-0367 | Ensure correct invoicing of PCF services | Infrastruktur - Referent
FF-HS-0368 | Negotiate new contract for security services | Infrastruktur - TL / PL
FF-IT-0110 | Automate Test Data Generation | IT - TL / PL
FF-IT-0111 | Insource bespoke developments | IT Business Process - Referent
FF-IT-0113 | Demigrate Dock’n’Roll | IT Operations - Expert
FF-IT-0114 | Eliminate GHA messaging cost | IT Operations - Referent
FF-IT-0115 | Implement CHAMP CCS Cost degression | Kapazitäts- und Netzwerkplanung - Referent
FF-IT-0116 | Eliminate MESX & SITA messaging cost | Kapazitäts- und Netzwerkplanung - TL
FF-IT-0121 | Stop Fair@Link Usage | Kommunikation - Referent
FF-IT-0122 | Reduce Service Provider Cost - FF (C40 M901) | Kommunikation - TL
FF-IT-0123 | Insource 3rd level support Cargo IT Planning | Luftsicherheit - Referent
FF-IT-0361 | Demigrate INCA & TAMS | Luftsicherheit - TL
FF-IT-0498 | Reduce Customs IT North America | Measure Coordination / Tracker
FF-ww-0323 | eFreight global rollout | Operational Ground Production - Expert
FF-ww-0324 | Reduce Cool ULD transport Cost | Operational Ground Production – Expert
FF-ww-0326 | Increase w/h efficiency @ ACF | Operational Ground Production - TL
FF-ww-0327 | Increase w/h efficiency in ORD | Organizational Development
FF-ww-0328 | 100% eFreight | Other
FF-ww-0330 | Reduce cool ULD demurrage cost | Produktmanagement - Referent
FF-ww-0331 | Reduce standard ULD lease cost | Produktmanagement - TL / PL
FF-ww-0332 | Reduce ULD repair cost | Program Steering
FF-ww-0333 | Reduce cost of loading accessories | Projektmanagement - PL
FF-ww-0335 | e-Import | Projektmanagement - Referent (PMO)
FF-ww-0336 | Abolish car tracks | Projektsteuerung / QM - Referent
FF-ww-0337 | Simplify cargo net storing | Projektsteuerung / QM - TL
FF-ww-0338 | Improve GHA connectivity | Prozesse Vertrieb - Referent
FF-ww-0339 | Reduce intra-logistics | Prozesse Vertrieb - TL
FF-ww-0340 | Manage shipment transport | Prozessmanagement - Referent
FF-ww-0342 | PPS@FRA (Transit) | Recht / Politik / Strategie / Umwelt - Referent
FF-ww-0344 | RPA / AI Autoreply at Servicecenter and CST | Recht / Politik / Strategie / Umwelt - TL
FF-ww-0348 | Global process adaptions | Sales Regionen
FF-ww-0349 | Project US Security | Strategy
FF-ww-0374 | e-RFS | Tech Ops - Referent
FF-ww-0376 | Self service terminals@JFK | Tech Ops - TL
FF-ww-0441 | LHM procurment tactics | Training / Schulung
FF-ww-0442 | Mobile digital handling | Transport Control - Referent
FF-ww-0514 | Move to 451 (FF) | Transport Control - TL
FF-ww-0515 | AUTOMATE IMPORT BROKER PROCESS (AUTO IQA) | Transport Management
FF-ww-0521 | PPS@Further Stations | Vertrieb - Referent
FF-XA-0307 | Close Guangzhou (CAN) - handling | Vertrieb - TL
FF-XD-0308 | Switch TXL, HAJ, BRE and LEJ to full GHA Setup | Vertriebssteuerung - Referent
FF-XE-0229 | Close Ashgabat (ASB) - handling | Vertriebssteuerung - TL
FF-XE-0230 | Reduce local H-managers Norway and Sweden | Wartung & Instandhaltung - Referent
FF-XE-0309 | Outsource airmail documentation VIE | Wartung & Instandhaltung - TL
FF-XL-0233 | Cancel yearly security maintenance contract in brazil
FF-XM-0238 | Cancel OAL handling at SHJ
FF-XM-0512 | Outsource JNB warehouse
FF-XU-0310 | Introduce automated accounting platforms
FF-XU-0311 | Consolidate manpower provider in ORD
FF-XU-0312 | Switch from landline to Skype
FF-XU-0313 | Reduce Overtime F/XU
FF-XW-0314 | Streamline handling setup AMS
FF-XW-0315 | No replacement of PAR GC-H